## Sheet1
1 | Create a general app framework using Flask/SocketIO | 5 | 1 | 1
2 | Create a general UI layout for the app | 4 | 1 | 1
3 | Allow the user to switch languages | 1 | 2 | 1
5 | Include a searchable cross-language dictionary | 1 | 3 | 1
7 | Design a framework for vocab units | 1 | 1 | 1
8 | Design a framework for grammar units | 1 | 1 | 1
13 | Design the framework for practicing conversations | 2 | 1 | 1
18 | Generate vocab/grammar quizzes (all one quiz) that randomly pull from vocab lists | 1 | 2 | 1
21 | Allow the user to converse with chatbots in specialized scenarios (English) | 2 | 1 | 1
6 | Create unit-based vocab lists | 2 | 1 | 2
9 | Populate a few vocab units (English) | 3 | 1 | 2
10 | Populate a few grammar units (English) | 3 | 1 | 2
11 | Populate a few vocab units (Russian) | 3 | 1 | 2
12 | Populate a few grammar units (Russian) | 3 | 1 | 2
14 | Create a few specialized scenarios to practice the unit vocab (e.g. convenience store, meeting a neighbor) (English) | 1 | 1 | 2
15 | Collect conversation transcripts for the specific scenarios (English) | 4 | 2 | 2
16 | Create a few specialized scenarios to practice the unit vocab (e.g. convenience store, meeting a neighbor) (Russian) | 1 | 1 | 2
17 | Collect conversation transcripts for the specific scenarios (Russian) | 5 | 2 | 2
22 | Allow the user to converse with chatbots in specialized scenarios (Russian) | 2 | 1 | 2
4 | Allow the user to create their own vocab flashcards | 2 | 4 | 3
19 | Provide user with a grade for/feedback on their responses in conversation (English) | 10 | 2 | 3
20 | Provide user with a grade for/feedback on their responses in conversation (Russian) | 10 | 2 | 3
23 | Allow user to create a profile with a username and password | 3 | 5 | 3
24 | Store user progress (quiz/conversation grades) | 1 | 5 | 3
ID | Story | Estimation (hours) | Priority (1-5) | Sprint When Finished
25
26
27
28
29
30
31
32
33